## Data
Risk Map in Excel
Risk Tracker
Risk ID | Title | Impact | Likelihood | Mitigation | Description | Evaluation | Response | Control Measure
R001 | Virtual machine stops working | 5 | 2 | Mine | Unable to access virtual environment to run the app | Would not be able to deploy or demonstrate the app | Have the app infrastructure available on more than one VM | Use infrastructure as code
R002 | Broken version deployed | 5 | 1 | Mine | Version of app with errors deployed | Would not be able to show all features; loss of confidence in app | Run tests and trial app before showcase. Revert to the most stable version if need be | Automate tests before deployment
R003 | Not able to meet the deadline for the project | 5 | 2 | Mine | Unable to complete all objectives before deadline | Project would be unfinished | Regular stable version updates so that clear progress is reported | Regular uploads to GitHub
R004 | Unable to install all desired infrastrucure before deadline | 3 | 5 | Mine | As the app becomes more complex, more time will be consumed on non-essential parts of the project | Project would meet expectations but not the full creative vision | Take regular screenshots of progress and functionality. | Finish project early so that I can add any additional features.
R005 | Unable to integrate CI pipeline fully | 5 | 3 | Mine | During the construction of the app, issues may arise connecting the different technologies. | Project would not be fully integrated. | Include as much information as possible regarding any errors, as it is possible it could be fixed quickly with a fresh pair of eyes. | Contact the trainer as much as possible when inegrating pipeline.
R006 | Project does not meet all requirements | 5 | 2 | Mine | Coding is relatively new to me, so it is possible that I may miss something key once the project has been submitted. | Project would only be partially completed. | Read over the project objectives and specifications regularly. | Follow trello board and keep an eye on burndown chart

## Risk Map
Risk Map in Excel
| 5 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| 4 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| 3 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
Likelihood → | 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
|  | 1 | 2 | 3 | 4 | 5
Impact →
Update Risk Data